## Pivot Analysis
Row Labels | Count of Task_ID | Row Labels | Average of Expected_Days | Average of Actual_Days | Average of DelayDays
Delayed | 33 | Customer Support | 5 | 6.5556 | 1.5556
On Time | 27 | Maintenance | 4.5455 | 5.7273 | 1.1818
Grand Total | 60 | IT Support | 3.9231 | 4.9231 | 1
|  | Administration | 4.4615 | 5.4615 | 1
Delay Rate | 55% | Compliance | 4.2857 | 5 | 0.71429
|  | Grand Total | 4.4 | 5.45 | 1.05

## Executive_Summary
Executive Summary - Operational Performance Analysis
This analysis examined operational task completion data to assess efficiency and idetify delay patterns. Overall performance analysis indicates that 55% of tasks were completed later than expected, suggesting systemic delays rather than isolated incidents. Task-type analysis shows that Customer Support tasks experience the greatest delays, with an average completion time 1.6 days later than expected, highlighting a potential operational bottleneck. Based on these findings, a targeted review of Customer Support workflows and ongoing monitoring of delay metrics by task type is recommended to improve overall operational efficiency.
Prepared by: Spencer Price
Tool Used: Microsoft Excel

## Operational_Data
Task_ID | Task_Type | Department | Assigned_Date | Completed_Date | Expected_Days | Actual_Days | Status | Priority | DelayDays
TASK-1001 | Administration | HR | 2025-08-06 | 2025-08-16 | 7 | 10 | Delayed | High | 3
TASK-1007 | Administration | Facilities | 2025-09-07 | 2025-09-12 | 6 | 5 | On Time | Low | -1
TASK-1011 | Administration | Operations | 2025-07-23 | 2025-07-28 | 6 | 5 | On Time | Medium | -1
TASK-1015 | Administration | Finance | 2025-08-20 | 2025-08-24 | 4 | 4 | On Time | High | 0
TASK-1020 | Administration | Operations | 2025-07-26 | 2025-08-01 | 3 | 6 | Delayed | High | 3
TASK-1022 | Administration | Operations | 2025-08-01 | 2025-08-07 | 4 | 6 | Delayed | High | 2
TASK-1023 | Administration | IT | 2025-09-21 | 2025-09-24 | 3 | 3 | On Time | Medium | 0
TASK-1040 | Administration | Operations | 2025-08-25 | 2025-08-28 | 1 | 3 | Delayed | Low | 2
TASK-1041 | Administration | HR | 2025-08-08 | 2025-08-17 | 7 | 9 | Delayed | Low | 2
TASK-1046 | Administration | Facilities | 2025-09-07 | 2025-09-14 | 7 | 7 | On Time | Medium | 0
TASK-1047 | Administration | IT | 2025-07-26 | 2025-07-27 | 2 | 1 | On Time | Medium | -1
TASK-1055 | Administration | Finance | 2025-08-12 | 2025-08-21 | 7 | 9 | Delayed | Medium | 2
TASK-1057 | Administration | Operations | 2025-08-17 | 2025-08-20 | 1 | 3 | Delayed | Medium | 2
TASK-1004 | Compliance | Operations | 2025-09-07 | 2025-09-14 | 7 | 7 | On Time | Low | 0
TASK-1010 | Compliance | Operations | 2025-09-16 | 2025-09-18 | 1 | 2 | Delayed | High | 1
TASK-1014 | Compliance | IT | 2025-07-10 | 2025-07-18 | 5 | 8 | Delayed | Medium | 3
TASK-1017 | Compliance | IT | 2025-09-08 | 2025-09-16 | 7 | 8 | Delayed | Low | 1
TASK-1019 | Compliance | HR | 2025-09-26 | 2025-09-28 | 2 | 2 | On Time | High | 0
TASK-1021 | Compliance | HR | 2025-09-04 | 2025-09-12 | 5 | 8 | Delayed | Medium | 3
TASK-1029 | Compliance | Facilities | 2025-09-17 | 2025-09-21 | 4 | 4 | On Time | Medium | 0
TASK-1033 | Compliance | Finance | 2025-08-28 | 2025-09-04 | 6 | 7 | Delayed | Medium | 1
TASK-1037 | Compliance | IT | 2025-09-06 | 2025-09-12 | 7 | 6 | On Time | Medium | -1
TASK-1038 | Compliance | Operations | 2025-08-11 | 2025-08-15 | 1 | 4 | Delayed | High | 3
TASK-1044 | Compliance | Finance | 2025-09-17 | 2025-09-20 | 4 | 3 | On Time | Medium | -1
TASK-1048 | Compliance | Finance | 2025-07-17 | 2025-07-20 | 3 | 3 | On Time | Medium | 0
TASK-1052 | Compliance | IT | 2025-08-25 | 2025-09-01 | 7 | 7 | On Time | High | 0
TASK-1053 | Compliance | Finance | 2025-07-08 | 2025-07-09 | 1 | 1 | On Time | Low | 0
TASK-1002 | Customer Support | Operations | 2025-07-21 | 2025-07-30 | 6 | 9 | Delayed | High | 3
TASK-1005 | Customer Support | HR | 2025-09-22 | 2025-09-30 | 5 | 8 | Delayed | High | 3
TASK-1006 | Customer Support | Finance | 2025-09-27 | 2025-10-04 | 7 | 7 | On Time | Medium | 0
TASK-1008 | Customer Support | IT | 2025-08-11 | 2025-08-13 | 2 | 2 | On Time | Medium | 0
TASK-1016 | Customer Support | HR | 2025-09-02 | 2025-09-09 | 6 | 7 | Delayed | Medium | 1
TASK-1034 | Customer Support | Operations | 2025-08-11 | 2025-08-18 | 5 | 7 | Delayed | High | 2
TASK-1035 | Customer Support | Operations | 2025-09-11 | 2025-09-20 | 7 | 9 | Delayed | Medium | 2
TASK-1039 | Customer Support | IT | 2025-07-31 | 2025-08-04 | 4 | 4 | On Time | Low | 0
TASK-1056 | Customer Support | Finance | 2025-07-20 | 2025-07-26 | 3 | 6 | Delayed | High | 3
TASK-1009 | IT Support | Operations | 2025-07-06 | 2025-07-13 | 5 | 7 | Delayed | Low | 2
TASK-1012 | IT Support | Operations | 2025-07-28 | 2025-07-30 | 2 | 2 | On Time | Medium | 0
TASK-1018 | IT Support | Facilities | 2025-09-11 | 2025-09-19 | 7 | 8 | Delayed | Low | 1
TASK-1024 | IT Support | Finance | 2025-08-10 | 2025-08-16 | 5 | 6 | Delayed | Medium | 1
TASK-1027 | IT Support | Operations | 2025-09-22 | 2025-09-28 | 4 | 6 | Delayed | Medium | 2
TASK-1028 | IT Support | Operations | 2025-07-07 | 2025-07-16 | 7 | 9 | Delayed | High | 2
TASK-1030 | IT Support | HR | 2025-08-10 | 2025-08-12 | 2 | 2 | On Time | Low | 0
TASK-1043 | IT Support | HR | 2025-08-10 | 2025-08-15 | 3 | 5 | Delayed | Low | 2
TASK-1045 | IT Support | Finance | 2025-08-05 | 2025-08-06 | 1 | 1 | On Time | Low | 0
TASK-1049 | IT Support | Operations | 2025-08-21 | 2025-08-22 | 1 | 1 | On Time | Medium | 0
TASK-1050 | IT Support | IT | 2025-07-07 | 2025-07-16 | 6 | 9 | Delayed | Medium | 3
TASK-1058 | IT Support | Finance | 2025-08-31 | 2025-09-06 | 6 | 6 | On Time | Low | 0
TASK-1060 | IT Support | Operations | 2025-08-19 | 2025-08-21 | 2 | 2 | On Time | High | 0
TASK-1003 | Maintenance | IT | 2025-08-29 | 2025-09-02 | 4 | 4 | On Time | Low | 0
TASK-1013 | Maintenance | Finance | 2025-08-23 | 2025-08-29 | 5 | 6 | Delayed | Low | 1
TASK-1025 | Maintenance | Finance | 2025-09-21 | 2025-09-28 | 5 | 7 | Delayed | High | 2
TASK-1026 | Maintenance | Finance | 2025-07-28 | 2025-08-03 | 6 | 6 | On Time | High | 0
TASK-1031 | Maintenance | Operations | 2025-09-01 | 2025-09-07 | 4 | 6 | Delayed | Low | 2
TASK-1032 | Maintenance | Finance | 2025-07-28 | 2025-08-01 | 1 | 4 | Delayed | Medium | 3
TASK-1036 | Maintenance | HR | 2025-08-27 | 2025-08-30 | 3 | 3 | On Time | High | 0
TASK-1042 | Maintenance | IT | 2025-09-12 | 2025-09-21 | 7 | 9 | Delayed | Low | 2
TASK-1051 | Maintenance | Finance | 2025-09-10 | 2025-09-19 | 7 | 9 | Delayed | Low | 2
TASK-1054 | Maintenance | Operations | 2025-09-03 | 2025-09-09 | 4 | 6 | Delayed | High | 2
TASK-1059 | Maintenance | Operations | 2025-08-12 | 2025-08-15 | 4 | 3 | On Time | Medium | -1